## HoneWeb Android app requirement
Application | Main Task | Task | Details | Owner | Sign off by/Date | Planned Start | Planned Finish | New Finish date if delay | Effort(Hours) | Dependency | Status | Comments | Actual Start | Actual Finish | Actual Effort
Plan Phase
1. Planning | 1.1 Project Plan |  |  | Johnson&Charlin
| 1.2 Replan |  |  | Johnson&Charlin
Requirement Phase
2. Main functions | 2.1 Welcome page |  | IBM HONE
2.2 Team introduction page
2.3 Function describe page
| 2.4 Main Page |  | All function with Buttons
2.5 Ooops page
3. Price | 3.1 Software page
3.2 Software result page
3.3 Software result details page
3.4 Hardware page
3.5 Hardware result page
4. Environment | 4.1 Set up the IBM Mobile environment
4.2 Confirm about the authentication way
5. Issue APP | 5.1 Issue APP to IBM APP Store

## HW Android App WBS First Cycle
Steps | Main Task | Task | Details | Owner | Sign off by/Date | Planned Start | Planned Finish | New Finish date if delay | Effort(Hours) | Dependency | Status | Comments | Actual Start | Actual Finish | Actual Effort
Plan Phase
1. Planning | 1.1 Project Plan |  |  | Johnson&Charlin |  | 2016-10-26 | 2016-11-01 | [5 empty] | 2016-01-13 | 2016-01-15 | 16
| 1.2 Replan |  |  | Johnson&Charlin |  | 2016-11-02 | 2016-11-04 | [5 empty] | 2016-01-25 | 2016-02-03 | 16
Requirement Phase
2. Main functions | 2.1 Welcome page |  | IBM HONE | Johnson&team | 2016.11.9 | 2016.11.7 | 2016.11.11
| 2.2 Team introduction page |  |  | Johnson&team | 2016.11.9 | 2016.11.7 | 2016.11.11
| 2.3 Function describe page |  |  | Johnson&team | 2016.11.9 | 2016.11.7 | 2016.11.11
| 2.4 Main Page |  | All function with Buttons | Johnson&team | 2016.11.9 | 2016.11.7 | 2016.11.11
| 2.5 Ooops page |  |  | Johnson&team | 2016.11.9 | 2016.11.7 | 2016.11.11
3. Environment | 3.1 Set up the IBM Mobile environment |  |  | Johnson&team | 2016.11.9 | 2016.11.7 | 2016.11.11
| 3.2 Confirm about the authentication way |  |  | Johnson&team | 2016.11.9 | 2016.11.7 | 2016.11.11
4. Issue APP | 4.1 Issue App to IBM App Store |  |  | Johnson&team | 2016.11.9 | 2016.11.7 | 2016.11.11
Environment Phase
IDE envrionment | Eclipse + ADT + SDK |  |  | Team | 2016.11.11 | 2016.11.4 | 2016.11.11
GitHub | Create GitHub environment |  |  | Charlin | 2016.11.14 | 2016.11.10 | 2016.11.15
| Set up GitHub process and familiar with the code management |  |  | Team |  | 2016.11.10 | 2016.11.16
Desin Phase
5. Common UI Style Design | 5.1 Icon, Style, Color, Size |  |  | CiCi |  | 2016.11.14 | 2016.11.25
6. Pages UI Design | 6.1 Welcome page |  |  | Jane |  | 2016.11.14 | 2016.11.25
| 6.2 Team introduction page |  |  | Wendy |  | 2016.11.14 | 2016.11.25
| 6.3 Function describe page |  |  | Ding |  | 2016.11.14 | 2016.11.25
| 6.4 Main Page |  |  | Peter |  | 2016.11.14 | 2016.11.25
| 6.5 Ooops page |  |  | Peter |  | 2016.11.14 | 2016.11.25
7. IBM Mobile Environment | 7.1 Set up the IBM Mobile environment |  |  | Wendy & Peter |  | 2016.11.14 | 2016.11.25
8. IBM Mobile authentication | 8.1 Confirm about the authentication way |  |  | Charlin |  | 2016.11.14 | 2016.11.25
Development Phase
10. Function Development | 10.1 Welcome page
10.2 Team introduction page
10.3 Function describe page
10.4 Main Page
10.5 Ooops page
11. IBM Mobile authentication | 11.1 Authentication User
12. Issue APP | 12.1 Issue App to IBM App Store
Test Phase
Test on the Mobile |  |  |  | team |  | 2017-05-04